## Sponsor Inputs
# | Epic | User Story | Priority | Planned Sprint | Status
1 | Create Account | As a customer, I want to create an account to be able to order food and track my order list in future. | 3 | 1 | Completed
2 | View Restaurants | As a customer, I want to have full access to all the available restaurants so that I can be able to order easily depends on the near by restaurants, comfortable prices and delivery estimated time. | 4 | 2 | Completed
3 | Search Restaurants | As a product owner, I want the customers to be able to have the easiest way to search for restaurants so that they can pick the best option available. | 4 | 3 | Completed
4 | View Menu | As a customer, I want to be able to view the menu so that I can choose my specific meal. | 5 | 4 | Completed
5 | Add to Cart | As a product owner, I want the customers to be able to add items to cart so that customers could add and remove the items easily. | 2 | 5 | Completed
6 | Purchase | As a product owner, I want the customer to be able to purchase so that they have the option to pay cash or online and confirm the order. | 3 | 6 | Completed
7 | Restaurant views order | As a product owner, I want the restaurant to view order so that they prepare the meals and track the customers orders in future. | 4 | 6 | Completed
8 | Restaurant marks order as delivered | As a product owner, I want the restaurant to marks order as delivered so that they can confirm the orders and continue to receive more orders. | 3 | 6 | Completed

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
| Create Account | As a customer, I want signup page so that include (First Name, Last Name, Email, Phone Number,Password) | high | Create Account | Create Account | TO DO
| Create Account | As a customer, I want Email Address verification page | medium | Create Account | Create Account | TO DO
| Create Account | As a customer, I want signin page so that include (Email or Phone Number,Password) | high | Create Account | Create Account | TO DO
| Create Account | SIT (System Integration Testing) | medium | Create Account | Create Account | TO DO
| Create Account | UAT(User Acceptance Testing) | medium | Create Account | Create Account | TO DO
| View Restaurants | Home page design | medium | View Restaurants
| View Restaurants | show the restaurant near by | medium | View Restaurants
| View Restaurants | show the restaurant categories | medium | View Restaurants
| View Restaurants | SIT (System Integration Testing) | medium | View Restaurants
| View Restaurants | UAT(User Acceptance Testing) | medium | View Restaurants
| Search Restaurants | search restaurant by name | medium | Search Restaurants
| Search Restaurants | search restaurant by category | medium | Search Restaurants
| Search Restaurants | search restaurant by city | medium | Search Restaurants
| Search Restaurants | search restaurant by language (Arabic-English) | medium | Search Restaurants
| Search Restaurants | SIT (System Integration Testing) | medium | Search Restaurants
| Search Restaurants | UAT(User Acceptance Testing) | medium | Search Restaurants
| View Menu | view the pics | medium | View Menu
| View Menu | view the name of the items | medium | View Menu
| View Menu | view the price of the items | medium | View Menu
| View Menu | SIT (System Integration Testing) | medium | Search Restaurants
| View Menu | UAT(User Acceptance Testing) | medium | Search Restaurants
| Add to Cart | cart page | medium | Add to Cart
| Add to Cart | item counter | medium | Add to Cart
| Add to Cart | price calculate | medium | Add to Cart
| Add to Cart | SIT (System Integration Testing) | medium | Add to Cart
| Add to Cart | UAT(User Acceptance Testing) | medium | Add to Cart
| Purchase | purchase page | medium | Purchase
| Purchase | total bill + any extra fees | medium | Purchase
| Purchase | add a payment methodes | medium | Purchase
| Purchase | pay with apple pay | medium | Purchase
| Purchase | pay with credit card | medium | Purchase
| Purchase | cash on delivery | medium | Purchase
| Purchase | SIT (System Integration Testing) | medium | Purchase
| Purchase | UAT(User Acceptance Testing) | medium | Purchase
| Restaurant views order | restaurant portal page design | high | Restaurant views order
| Restaurant views order | customer comment spot | medium | Restaurant views order
| Restaurant views order | SIT (System Integration Testing) | medium | Restaurant views order
| Restaurant views order | UAT(User Acceptance Testing) | medium | Restaurant views order